## Slide 1: IAMS Change Management Implementation briefing Date: 8/16/18

## Slide 2
OUTLINE
  TERMS
  BACKGROUND
  CHANGE MANAGEMENT
  CMB WAY-AHEAD

## Slide 3
DEFINITIONS
Terms | Description
Baseline | A snapshot in time that provides a building block for subsequent development work. Listing of approved configuration items.
Change Management | A functional element of configuration management that involves the evaluation, coordination, approval/disapproval and implementation after formal establishment of the configuration identification.
Change Management Board (CMB) | A group of members responsible for evaluation and disposition of changes to configuration items. CMB has configuration control authority (CCA) over baseline items.
Modification Request (MR) | A CM form used to establish a baseline and to control changes to Configuration Items (CIs).
Product | An item that consist of one or more of the following: hardware, software, firmware, facilities, data, material, services, techniques, personnel, and process. (Reference: EIA 632, Processes for Engineering a System)

## Slide 4
Change Management is currently not implemented on IAMS
Without Change Management important changes can be implemented with no formal record kept, changes such as:
  What change was made
  Why was the change made
  Who requested the change
  What products/components are affected by the change
  What is the impact (i.e. schedule, resource, cost) of the proposed change
BACKGROUND

## Slide 5
JIRA is a Project Management tool for Agile teams, it’s not a Change Management tool
BACKGROUND (cont.)

## Slide 6
BACKGROUND (cont.)
The Fiscal Year Quarterly Build Forecast are project management artifacts

## Slide 7
BACKGROUND (cont.)
The IAMB PMO Program Plan is a requirements artifact

## Slide 8
  IN NUTSHELL:
    JIRA is not a Change Management tool
    The IAMB PMO Program Plan is not a CM artifact
    The FY18 Quarterly Build Forecasts are not CM artifacts
    The Regression Readiness Review (R3) Board is not a Change Management Board (CMB)
BACKGROUND (cont.)

## Slide 9
  It’s the systematic evaluation of proposed changes to configuration items
  It’s a major element of CM that formally establish baselines
  It’s the gatekeeper for controlling changes to configuration items
What is Change Management?

## Slide 10
  A process to:
    Understand impact(s)
    Obtain informed consent (impact analysis)
    Coordinate and communicate changes
What is Change Management?
(cont.)

## Slide 11
  Manages proposed changes via a common form:
    Modification Request (MR)
    Change Request (CR)
    Engineering Change Proposal (ECP)
    Request for Change (RFC)
What is Change Management?
(cont.)

## Slide 12
To maintain product integrity throughout the product’s lifecyle
  Consistency is important in:
    Chairman and Membership
    Administration
      Crisp conduct (all issues resolved prior to board)
      CMB is not Technical Exchange Meeting
      Clarity and promptness of Minutes and action item distribution
      Timely follow-up of required actions
Change Management Board (CMB) – Responsibilities

## Slide 13
Process Modification Request (MR)
  Evaluate MRs for impact assessments
  Disposition MRs (approve or disapprove)
Change Management Board – Responsibilities (cont.)

## Slide 14
Change Management Board (CMB) – Membership
CMB Role | Functional Area
Chair | PM
CMB Secretariat (Facilitator) | CM
Voting members | CALs
Voting member | OPS Lead
Non-voting member | Software Tester
Non-voting member | Release Manager
Non-voting member | Stakeholder

## Slide 15
How does the CMB work?
A Modification Request form is completed and provided to CMB secretariat
CMB secretariat reviews MR for completion
CMB secretariat distributes MR package to CMB members for review, impact assessment and recommendations
CM distributes CMB Agenda
CMB meeting scheduled to review Agenda items
CMB disposition MR
Meeting minutes are prepared to convey approval/disapproval decisions from the Board

## Slide 16
MR Form basics
Analysis
  Priority
  Is change compatible with Project Scope
  Major change (require customer approval)
  Minor change (impact internal or no baseline)
Decision
  Approve or Reject
Identification
  CM Tracking #
  Submitter name
  Date
  Description
    Justification
    Benefits
    Operation context
    Impact to user(s)

## Slide 17
BACKUP SLIDES

## Slide 18
MR Form basics (cont.)
What is impacted
  Real issue (hw, sw, doc, etc)
Effectivity
  When does this change start/stop
Root cause
Estimate to complete

## Slide 19
MR candidate – Scenario 1
MR submitted for a conf item (Prod Baseline)
MSS 3.0.1 Release
  DSEE 1.3.0
  DSEE 1.4.0
  EGW 2.1.0
    CRL Service 1.0.0
    OpenPTK 2.0.0
  Nagios 2.3.0
  WFTrust 4.0.0
  Targeted Environment: MSS

## Slide 20
MR candidate – Scenario 2
MR submitted for a conf item (Stack Product)
EGW 2.1.0 Release
    CRL Service 1.0.0
    FTS 3.0.0
    OpenPTK 2.0.0
    PDP 2.1.0
    SCIM 3.2.0
  Targeted Environment(s):
  MSS, IAMS C2S, IAMS CME

## Slide 21
MR candidate – Scenario 3
MR submitted for a conf item (Stand-alone)
Omni v1.0
  Targeted Environment(s):
  IAMS C2S

## Slide 22
Change Management Board (CMB) – Process Flow
CMB evaluates MR
CMB approve or Reject MR
MR Approved
Add CI to CM baseline
MR Rejected
MR returned to submitter

## Slide 23
CMB Benefits
Improves:
Team communication
Provides product visibility
Maintains product integrity
Control changes
Decreases:
Rework
Confusion
Project risk

## Slide 24
CMB Way-Ahead
Recommend baselining the IAMS Configuration Management Plan (CMP)

## Slide 25
Question or Concerns
Suggestions ?
Comments ?
Recommendation ?

## Slide 26
CMB and R3
Gap Analysis
CMB (Membership) | R3 Board (Membership) | Michele’s Comments
Chair | Chair | No change.
CMB Secretariat (Facilitator) | CMB Secretariat (Facilitator) | No change.
Voting members | Voting members | No change.
Voting member | Voting member | No change.
Non-voting member | Non-voting member | No change.
Non-voting member | Non-voting member | No change.
SETA (optional) | SETA | This is the only change btw board members

## Slide 27
CMB and R3
Gap Analysis
CMB functions | R3 Board functions | Michele’s Comments
The CMB is initiated before Engineering work starts and remains engaged through the product lifecycle | The R3 process starts after Engineering work is completed . | The CMB enables planning upfront. Plan the work, work the plan.
Prior to Engineering work starting, all relevant project teams members review and approve proposed change(s). Upfront coordination enables RM to know when work starts, gives estimate deployment schedule, work priority, and cross team eval of cost, resource, security, schedule, and technical impacts. | Impact assessment done by Engineer and CAL (i.e. stovepipe). The R3 process ends after product is approved for promotion to high side network. | The R3 does not enable collective analysis (CALs, OPS, RM) to get on the same page before work begins or even during development work. For instance, if a product is withdrawn for whatever reason, there is no formal why to inform other project members. If a product is renamed, there is no formal why to learn the new name change. CM and RM need to know of product changes because Jim maintains a software listing of Products delivered to various customers and Lisa (RM) would need to remove the product from her Deployment plan. CM currently learns of changes through the grapevine, informally and it’s believed the RM learns of changes from looking at the quarterly build page and/or attending various meetings.

## Slide 28
CMB and R3
Gap Analysis
CMB functions | R3 Board functions | Michele’s Comments
MR form: Formally establishes a Baseline and manages change to delivered software and documents. | R3: Does not establish baselines. | The MR form and its associated documentation tracks product changes (i.e. who, what, when, why,) throughout product lifecycle. The MR form traces requirement, software, and documentation in one central location.

## Slide 29
CMB and R3
Gap Analysis
CMB functions | R3 Board functions | Michele’s Comments
 | R3 page: Establishes when the software and document is ready for review to move from Dev (network) to Prod (network) | The R3 no longer track product changes after R3 approval. For example, if an Install guide has errors detected on high side, a revised install guide (new product) does not go back to the R3 for approval. The R3 page formally tracks changes that Env personnel find in Regression environment. CM: Doc and Code are tracked via Pre-FAT and FAT folders. There is not a change form that maps to the approved product. Multiple copies of documents are found on Shared drive. The JIRA ticket has the R3 approval status for items boarded.

## Slide 30
CMB and R3
Gap Analysis
CMB functions | R3 Board functions | Michele’s Comments
Status Accounting: Formal Meeting Minutes are prepared that reflect CMB approval of Modification Request and applicable discussions. Minutes are formally CM records. | Status Accounting: No R3 meeting minutes prepared. | R3 facilitator enters the board decisions in JIRA ticket. (approve or reject).